Company Name: Corporate

Author(s): Brad Bergeron, Stephanie Smith, Yuan Tu

Version #: 0.7

Date created: 9/18/2015

Date updated: 10/20/2015

Project Plan

Table Of Contents

Introduction 2

Master Project Schedule 3

Estimation Worksheet 3

Roles and Responsibilities 5

Risk Management Plan 5

Process Model Implementation ` 7

Collect Requirements for initial set of Functions 7

References 7

Index 8

**Audience:** Raman Aravamudhan, Aashay Borgaonkar

**Distribution List:** Corporate, Raman Aravamudhan, and Aashay Borgaonkar

**Scope of Document:** This Document will cover the different areas of our Project Plan. The schedule for the length of the project, estimation worksheet will define the amount of time it will for each part of the project, the roles and responsibilities for each iteration, how we plan to handle and prevent certain risks, the way we plan to implement our process model, and last how we plan to collect our requirements on a weekly bases.

**Introduction**

The project plan must go over every aspect of the project to assure nothing is left uncovered. This document will continue to change and develop as the project continues. the first area we shall cover is the schedule of when we plan to get stuff done and expand from there.

**Master Project Schedule**

|  |  |
| --- | --- |
| **Task** | **Date** |
| Complete Project Plan (V 0.3) | 10/1/2015 |
| Iteration #1: generate login and signup page, add functionality behind these pages (store users in database with encrypted password) | 10/8/2015 |
| High Level Design (V 0.1) | 10/17/2015 |
| Task Plan (V 0.1) | 10/17/2015 |
| User Requirement Specification (URS) and Software Specifications (SRS) → (V 0.1) | 10/17/2015 |
| Iteration #2: implement a data driven process model selection and fine tune interface | 10/22/2015 |
| Iteration #3: implement task manager and security | 11/5/2015 |
| Iteration #4: fine tune the whole product | 11/19/2015 |

**Estimation Worksheet**

|  |  |  |  |
| --- | --- | --- | --- |
| **Component** | **Complexity** | | |
|  | **Low** | **Average** | **High** |
| **EI** | 3 | 4 | 6 |
| **EO** | 4 | 5 | 7 |
| **EQ** | 3 | 5 | 6 |
| **ILF** | 5 | 7 | 10 |
| **EIF** | 7 | 10 | 15 |

**FPA scale**

**Iteration #1**

Refine this using FPA estimation once requirements are gathered

Functions

Home Page: Login boxes, and sign up drop down menu

Team Member signup page: First Name, Last Name, Phone Number, Address, Gender, Birth date, Email, Username

Team Leader sign up page: Same as Team Member, plus Leader Log In Box

Admin sign up page: Same as Team Member, plus Admin Login Box

Database Storing: Communicating with sql, and storing in three tables.

Password encryption: Part of Database set up

More about signup pages: Make sure password has captial letter and a digit, Email Verification

EI (External Inputs)- 3 (team member, team leader, administrator)

EO (External Outputs) - 0 (none of the data inputted is creating a report of any kind)

EI (External Inquiry) - 2 (homepage and a signup page)

ILF (Internal Logic Files) - 2 (team member RDB table, team leader RDB table, administrator RDB tabler)

ELF (External Interface Files) - 0 (none of the data is being exchanges with other systems

|  |  |  |
| --- | --- | --- |
| **Category** | **Multiplier** | **Weight** |
| **EI** | 3 | 3 |
| **EO** | 0 | 4 |
| **EQ** | 2 | 3 |
| **ILF** | 2 | 5 |
| **EIF** | 0 | 7 |

FPA=3\*3+0\*4+2\*3+2\*5+0\*7

FPA=25

We are estimating that each function point is equivalent to 4 hours of work in ASP.NET.

25\*4=**100 hours of work**

**Iteration #2**

Functions:

Project Pages Other: List of projects they are in, sign up for a project

Submitted projet page: Save process or Overwrite for something else

Process Model Survey for Leader

Process Model Selection

Override the app’s process model decision

Email Verification

Navigation Tabs for Process Model Survey

Add Project if you are a leader

View your projects for member/leader

EI (External Inputs)- 4 (create project, view project, submit questions, verify email, navigation tabs)

EO (External Outputs) - 1 (suggested process model)

EQ (External Inquiry) - 2 (leader profile, admin profile, member profile, join project)

ILF (Internal Logic Files) - 10 (QuestionsTable, MutlipleChoiceAnswerTable, 6 ProcessModelTables, TrainingDataTable, UserProjectTable)

ELF (External Interface Files) - 1 (email verification)

|  |  |  |
| --- | --- | --- |
| **Category** | **Multiplier** | **Weight** |
| **EI** | 4 | 3 |
| **EO** | 1 | 7 |
| **EQ** | 2 | 3 |
| **ILF** | 10 | 5 |
| **EIF** | 1 | 10 |

FPA= 4\*3 + 1\*7 + 2\*3 + 10\*5 + 1\*10

FPA = 85

We are estimating that each function point is equivalent to 4 hours of work in ASP.NET.

85\*4=**340 hours of work**

**Iteration #3**

Functions:

Create Calendar for each project

Admin/Leader/Member can view calendar

Admin/Leader/Member can add events to calendar

Admin/Leader/Member can remove events from calendar

Leader must approve calendar changes from members/admin

Admin can add members to projects

Admin can assigns roles to members

Admin can demote leaders

EI (External Inputs)- 3 (assign roles, demote leaders, approve events)

EO (External Outputs) - 1 (Calendar view, Edit members view, Change member roles view)

EI (External Inquiry) - 2 (view roles/responsibilities, view members)

ILF (Internal Logic Files) - 2 (ProjectUser Table, Project Calendar Table)

ELF (External Interface Files) - 0 (none of the data is being exchanges with other systems)

|  |  |  |
| --- | --- | --- |
| **Category** | **Multiplier** | **Weight** |
| **EI** | 3 | 3 |
| **EO** | 1 | 5 |
| **EQ** | 2 | 3 |
| **ILF** | 2 | 10 |
| **EIF** | 0 | 7 |

FPA=3\*3+1\*5+2\*3+2\*10+0\*7

We are estimating that each function point is equivalent to 4 hours of work in ASP.NET.

40\*4=**160 hours of work**

**Iteration #4:**

Functions:

Forgot Password

Alert boxes

Style

EI (External Inputs)- 2 (forgetful user, user confirming alert actions)

EO (External Outputs) - 0 (no reports are formed from incoming data)

EI (External Inquiry) - 3 (return user password, forgot password view, alert boxes)

ILF (Internal Logic Files) - 0 (no new data is needed)

ELF (External Interface Files) - 0 (none of the data is being exchanges with other systems)

|  |  |  |
| --- | --- | --- |
| **Category** | **Multiplier** | **Weight** |
| **EI** | 2 | 3 |
| **EO** | 0 | 4 |
| **EQ** | 3 | 3 |
| **ILF** | 0 | 5 |
| **EIF** | 0 | 4 |

**Roles and Responsibilities**

**Iteration #1:**

Brad - Team Leader

Steph - Client Communicator

Yuan - Documentor

**Iteration #2:**

Brad - Documentor

Steph- Team Leader

Yuan - Client Communicator

**Iteration #3:**

Brad - Client Communicator

Steph -Documentor

Yuan - Team Leader

**Iteration #4:**

Brad - Team Leader

Steph - Client Communicator

Yuan - Documentor

**Risk Management Plan**

**Risk #1:**

Risk: A team member is going to be out of town for a meeting

Solution: The rest of the team will continue to work without them. The team member leaving will make sure everything on there end is ready before the meeting. Than when they return the rest of the team will bring them up to speed and help them establish new tasks for them.

**Risk #2:**

Risk: Not sure how to use the proper tools to complete the project.

Solution: When considering the tools we have available we will do extensive research into each of our tools to insure that no extra costs or limitations will stop us from accomplishing our project goal.

**Risk #3:**

Risk: Having messy and unorganized code is another risk.

Solution: Before any code is writing we will meet up and decided on our formating for our code.

**Risk #4:**

Risk: Handing a continually changing system requirements.

Solution: the agile Scrum process model allow us generate different requirements each Sprint Planning meeting from our customer.

**Risk #5:**

Risk: poorly measure sprint progress.

Solution: We are going to have sprint review meetings at the end of each sprint, and apply a sprint review technique for tracking the progress accurately.

**Risk #6:**

Risk: Failure to gain user commitment.

Solution: We have assigned a Client Communicator who is mainly responsible to communicate well with our client. And other team members would also help the our understand the requirements well. If there is any requirement we feel unclear or cannot be implemented, we should communicate with our client on time.

**Risk #7:**

Risk: Team member is dropping

Solution: We will split up the work for the remainder iteration than talk to Ramen about the requirements of the project for two people.

**Risk #8:**

Risk: One of the Team Members is not contributing to the project.

Solution: We will discuss what to do with Ramen.

**Risk #9:**

Risk: Data is lost.

Solution: We keep back up on all tables of data that need to be saved

**Process Model Implementation**

We’ve chosen to follow an Agile process model, and we will be implementing it using SCRUM. We will make a product backlog by 10/1/2015, and begin our first iteration on 9/4/2015. We will have four iterations. We’ll meet 3 times a week during each sprint, and conclude each iteration with a sprint review and sprint retrospective meeting.

**Collect Requirements for initial set of Functions**

Meetings with Aashay will occur every Thursday at 2pm, we will use this time to gather the requirements for the project. After the meeting we will start work on the new requirements, if any more questions arise we will ask them in the lecture ran by Raman. We will have a short meeting after Monday's lecture to make sure everyone is on the same page. Than we will have one more meeting Tuesday at 2pm to make sure we are all ready for another meeting with Aashay. This will be our process for collecting and understanding the requirements.

**References**

[1]<http://www.softwaremetrics.com/fpafund.htm> (9/21/15)

[2]<https://dev.mysql.com/doc/refman/5.1/en/encryption-functions.html> (9/24/15)

**Index**

Author’s 1

Estimation 3

Leader’s 5

Risk’s 5

Requirements 7

Schedule 3

FPA 3